# Your Path to a Self-Funded Plan

This is the full path from today to go-live. Five phases, each with its own short checklist.

| 1 | Kickoff & Implementation Calls | Weeks 1-4 |
| --- | --- | --- |
| 2 | Document Signatures | Weeks 2-5 |
| 3 | Open Enrollment | Weeks 4-9 |
| 4 | Finance Workstream | Weeks 4-7 |
| 5 | Go-Live | Effective Date |

| Full Checklist Everything in one place: calls, documents, and tasks across every team. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1 |  | Kickoff Calls |  |  |  |
| ITEM |  |  | WHAT THIS COVERS |  | RESPONSIBLE PARTY |
| TPA & Benefit Design Calls |  |  | Finalizes plan design and claims setup with your TPA |  | Client HR + CCIG |
| PBM Implementation Calls |  |  | Sets up your pharmacy formulary and member ID cards |  | Client HR + CCIG |
| Cost Containment Vendor Calls |  |  | Kicks off each Savings Engine vendor you selected |  | Client HR + CCIG |
| COBRA / FSA / HSA Calls |  |  | Transitions COBRA and FSA/HSA administration to the new plan |  | Client HR + CCIG |
| Banking Implementation Calls |  |  | Sets up claims funding with your TPA and bank |  | Client Finance + CCIG |
| Coverage Determination Calls (Optional) |  |  | Optional review of how high-cost claims will be paid |  | Client Finance |
| 2 | Document Signatures |  |  |  |  |
| ITEM |  |  | WHAT THIS COVERS | RESPONSIBLE PARTY | SIGNER |
| TPA Admin Service Agreement |  |  | The core contract governing claims administration | Client Executive/Finance | CFO / Authorized Signer |
| Stop-Loss Quote |  |  | Locks in your stop-loss pricing and terms | Client Executive/Finance | CFO / Authorized Signer |
| Stop-Loss Policy |  |  | The binding policy that pays claims above deductible | Client Executive/Finance | CFO / Authorized Signer |
| PBM Master Agreement |  |  | Governs pharmacy pricing and rebate terms | Client Executive/Finance | CFO / Authorized Signer |
| PBM Implementation Manual |  |  | Confirms formulary and prior authorization rules | Client Executive/Finance | CFO / Authorized Signer |
| Captive Agreement |  |  | Governs your participation in the group captive | Client Executive/Finance | CFO / Authorized Signer |
| Captive Capital Invoice |  |  | Your required capital contribution to the captive | Client Finance | CFO / Authorized Signer |
| Savings Engine Agreement - CancerCare |  |  | Enrollment agreement with CancerCare | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - eHealth |  |  | Enrollment agreement with eHealth | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - First Stop Health |  |  | Enrollment agreement with First Stop Health | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - Found |  |  | Enrollment agreement with Found | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - HUSK |  |  | Enrollment agreement with HUSK | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - Lyra Select |  |  | Enrollment agreement with Lyra Select | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - The Phia Group |  |  | Enrollment agreement with The Phia Group | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - Progeny Health |  |  | Enrollment agreement with Progeny Health | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - Renalogic |  |  | Enrollment agreement with Renalogic | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - Rightway |  |  | Enrollment agreement with Rightway | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - SmartConnect (powered by SmartMatch) |  |  | Enrollment agreement with SmartConnect (powered by SmartMatch) | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - Springbuk |  |  | Enrollment agreement with Springbuk | Client Executive/Finance | CFO / Authorized Signer |
| Savings Engine Agreement - Valenz Health |  |  | Enrollment agreement with Valenz Health | Client Executive/Finance | CFO / Authorized Signer |
| 3 | Build & Configure |  |  |  |  |
| ITEM |  |  | WHAT THIS COVERS |  | RESPONSIBLE PARTY |
| Build HRIS for Open Enrollment |  |  | Loads new plan options and rates into your HRIS |  | Client HR |
| Coordinate Open Enrollment Dates/Times |  |  | Locks the open enrollment window and meeting schedule |  | Client HR |
| Review Open Enrollment Communications & Materials |  |  | Approves employee enrollment guides and emails |  | Client HR |
| Complete Open Enrollment Eligibility File |  |  | Submits the census file that loads member records |  | Client HR |
| 4 | Finance Workstream |  |  |  |  |
| ITEM |  |  | WHAT THIS COVERS |  | RESPONSIBLE PARTY |
| Establish Bank Account for Benefits |  |  | Opens the account that funds claims payments |  | Client Finance |
| Review Sample Check Registers |  |  | Confirms your claims funding and reporting format |  | Client Finance |
| 5 | Go-Live & Cost Containment / Savings Engine Enrollment |  |  |  |  |
| ITEM |  |  | WHAT THIS COVERS |  | RESPONSIBLE PARTY |
| Complete Enrollment - CancerCare |  |  | Activates CancerCare for your members |  | Client HR |
| Complete Enrollment - eHealth |  |  | Activates eHealth for your members |  | Client HR |
| Complete Enrollment - First Stop Health |  |  | Activates First Stop Health for your members |  | Client HR |
| Complete Enrollment - Found |  |  | Activates Found for your members |  | Client HR |
| Complete Enrollment - HUSK |  |  | Activates HUSK for your members |  | Client HR |
| Complete Enrollment - Lyra Select |  |  | Activates Lyra Select for your members |  | Client HR |
| Complete Enrollment - The Phia Group |  |  | Activates The Phia Group for your members |  | Client HR |
| Complete Enrollment - Progeny Health |  |  | Activates Progeny Health for your members |  | Client HR |
| Complete Enrollment - Renalogic |  |  | Activates Renalogic for your members |  | Client HR |
| Complete Enrollment - Rightway |  |  | Activates Rightway for your members |  | Client HR |
| Complete Enrollment - SmartConnect (powered by SmartMatch) |  |  | Activates SmartConnect (powered by SmartMatch) for your members |  | Client HR |
| Complete Enrollment - Springbuk |  |  | Activates Springbuk for your members |  | Client HR |
| Complete Enrollment - Valenz Health |  |  | Activates Valenz Health for your members |  | Client HR |