## Instructions
Self-Funded Transition & Optimization Roadmap Tool
CCIG ¦ Internal Planning Tool
What this is
One selection on the Client Setup tab drives everything else: a visual roadmap cover page, and four short, audience-specific checklists (HR, Finance, Signing, and the Full Roadmap for anyone who wants everything). Each checklist item is a single scannable line; click the small [+] to its left to expand the full explanation only when you need it.
How to use it, in order
| 1. Client Setup | Enter the client's name and engagement type, then mark Yes/No for every plan component and Savings Engine vendor. This is the only tab you edit per client.
| 2. Roadmap Overview | The client-facing cover page: a visual timeline plus one-click links into each checklist. This is what you lead with.
| 3. HR / Finance / Signing Checklists | Short, audience-specific checklists that rebuild themselves from your Setup selections. Not-applicable items grey out automatically; click the Applicable filter and choose Yes for the clean client view. Expand any row's [+] for the full explanation.
| 4. Full Roadmap | The same content, unfiltered by audience, for anyone who wants the complete picture in one place.
| 5. Document & Task Library | The master content behind every checklist. Edit Description / Short Line / What to Expect here to refine language; changes flow into every future roadmap automatically.
| 6. Project Tracker | Your own internal status rollup. Not meant for the client.
Legend
Yellow = a cell you fill in or select
Grey = not applicable to this client (auto-calculated). Click the Applicable filter above the table and choose Yes to hide these rows.
| [+] | Click to expand the full explanation for that line
Reusing this for a new client
Save a copy of this workbook per client (e.g. "Acme Co - SF Transition Roadmap.xlsx"). Reset the Client Setup tab, and every other tab rebuilds itself.

## Client Setup
Client Setup
The only tab you edit per client. Everything else builds itself from here.
| Client Name | Example Employer, Inc.
Plan / Renewal Effective Date
| Prepared By | CCIG Benefits Team
Date Prepared
| Engagement Type | New to Self-Funding
CORE PROGRAM COMPONENTS
| Key | Component | Include?
| TPA_ADMIN | TPA Administrative Services | Yes
| STOP_LOSS | Stop-Loss Coverage | Yes
| PBM | Pharmacy Benefit Manager (PBM) | Yes
| CAPTIVE | Captive Participation | No
COST CONTAINMENT / SAVINGS ENGINE SOLUTIONS
| Key | Vendor / Solution | Include?
| CC_CANCERCARE | CancerCare - cancer care navigation | No
| CC_EHEALTH | eHealth - Medicare/ACA enrollment | No
| CC_FIRSTSTOP | First Stop Health - virtual primary/urgent care | No
| CC_FOUND | Found - weight & GLP-1 cost management | No
| CC_HUSK | HUSK - wellness (nutrition, mental health, rewards) | No
| CC_LYRA | Lyra Select - mental health | No
| CC_PHIA | The Phia Group - benefit compliance support | No
| CC_PROGENY | Progeny Health - neonatal intensive care management | No
| CC_RENALOGIC | Renalogic - chronic kidney disease & dialysis | No
| CC_RIGHTWAY | Rightway - surgeries, imaging & care navigation | No
| CC_SMARTCONNECT | SmartConnect (powered by SmartMatch) - Medicare enrollment | No
| CC_SPRINGBUK | Springbuk - health data analytics | No
| CC_VALENZ | Valenz Health - cost containment & claims | No
OPTIONAL ITEMS
| Key | Item | Include?
| FIN_COVERAGE_CALL | Finance: Coverage Determination Calls (optional) | No
CALCULATED (do not edit)
| ANY_CC | Any Cost Containment / Savings Engine solution selected? | No

## Roadmap Overview
Your Path to a Self-Funded Plan
Prepared for Example Employer, Inc. ¦ New to Self-Funding
This is the full path from today to go-live. Five phases, each with its own short checklist. Nothing below requires more than a click to open, and every item tells you what it is and what to expect before you need to ask.
Jump to your checklist
→ HR Checklist
Open enrollment setup and vendor calls
→ Finance Checklist
Banking setup and funding calls
→ Signing Checklist
Every document your CFO or Authorized Signer needs
→ Full Roadmap
Everything, across every team, in one place

## HR Checklist
HR Checklist
Prepared for Example Employer, Inc. ¦ New to Self-Funding
Your open enrollment setup and vendor calls, in order. Once Setup is finished, click the Applicable filter above and choose Yes to hide anything that doesn't apply.
Status | Item | What This Covers | Applicable? | Due Date
1. KICKOFF & IMPLEMENTATION CALLS
Not Started | TPA & Benefit Design Calls | Finalizes plan design and claims setup with your TPA | Yes
Why it matters: Kickoff calls with the Third Party Administrator to finalize plan design, eligibility rules, and claims administration setup ahead of the effective date. What to expect: 2-4 sessions of 60-90 minutes over the first 3-4 weeks. Have current plan documents and eligibility file specs ready.
Not Started | PBM Implementation Calls | Sets up your pharmacy formulary and member ID cards | Yes
Why it matters: Implementation calls with the Pharmacy Benefit Manager to configure the formulary, prior authorization rules, and member ID cards. What to expect: 2-3 calls led by the PBM's implementation team. HR confirms member eligibility feed timing.
Not Started | Cost Containment Vendor Calls | Kicks off each Savings Engine vendor you selected | No
Why it matters: Individual kickoff calls with each selected Savings Engine vendor to set up enrollment, eligibility feeds, and member communications. What to expect: One call per selected vendor, typically 30-45 minutes, scheduled across the first month.
Not Started | COBRA / FSA / HSA Calls | Transitions COBRA and FSA/HSA administration to the new plan | Yes
Why it matters: Setup calls with the COBRA administrator and FSA/HSA vendor to transition existing participants and establish new account administration. What to expect: One call per vendor. HR provides the current COBRA participant list and FSA/HSA balances for transition.
3. HR WORKSTREAM - OPEN ENROLLMENT SETUP
Not Started | Build HRIS for Open Enrollment | Loads new plan options and rates into your HRIS | Yes
Why it matters: Configure the HR information system to reflect new plan options, rates, and eligibility rules ahead of open enrollment. What to expect: HR-owned. CCIG provides plan design specs to support setup.
Not Started | Coordinate Open Enrollment Dates/Times | Locks the open enrollment window and meeting schedule | Yes
Why it matters: Finalize the open enrollment window and schedule employee meetings or webinars. What to expect: Lock this in early; it drives every other communication deadline.
Not Started | Review Open Enrollment Communications & Materials | Approves employee enrollment guides and emails | Yes
Why it matters: Review and approve employee-facing enrollment guides, emails, and presentation materials before distribution. What to expect: CCIG drafts the first version; HR reviews for accuracy and tone.
Not Started | Complete Open Enrollment Eligibility File | Submits the census file that loads member records | Yes
Why it matters: Finalize and submit the eligibility census file the TPA and vendors use to load member records. What to expect: The single most time-sensitive HR deliverable. A late file delays ID cards and vendor access for members.
5. COST CONTAINMENT / SAVINGS ENGINE ENROLLMENT
Not Started | Complete Enrollment - CancerCare | Activates CancerCare for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with CancerCare so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - eHealth | Activates eHealth for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with eHealth so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - First Stop Health | Activates First Stop Health for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with First Stop Health so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Found | Activates Found for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Found so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - HUSK | Activates HUSK for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with HUSK so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Lyra Select | Activates Lyra Select for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Lyra Select so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - The Phia Group | Activates The Phia Group for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with The Phia Group so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Progeny Health | Activates Progeny Health for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Progeny Health so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Renalogic | Activates Renalogic for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Renalogic so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Rightway | Activates Rightway for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Rightway so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - SmartConnect (powered by SmartMatch) | Activates SmartConnect (powered by SmartMatch) for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with SmartConnect (powered by SmartMatch) so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Springbuk | Activates Springbuk for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Springbuk so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Valenz Health | Activates Valenz Health for your members | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Valenz Health so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.

## Finance Checklist
Finance Checklist
Prepared for Example Employer, Inc. ¦ New to Self-Funding
Banking setup and funding calls. Once Setup is finished, click the Applicable filter above and choose Yes to hide anything that doesn't apply.
Status | Item | What This Covers | Applicable? | Due Date
1. KICKOFF & IMPLEMENTATION CALLS
Not Started | Banking Implementation Calls | Sets up claims funding with your TPA and bank | Yes
Why it matters: Calls with the TPA and bank to set up the claims funding account, wire/ACH authorization, and daily funding process. What to expect: 1-2 calls. Finance should have bank signer authorization ready in advance.
Not Started | Coverage Determination Calls (Optional) | Optional review of how high-cost claims will be paid | No
Why it matters: Optional calls where Finance reviews how specific high-cost claims will be adjudicated under the new plan design. What to expect: Scheduled only if Finance opts in on the Setup tab; typically one call.
2. DOCUMENTS TO SIGN
Not Started | Captive Capital Invoice | Your required capital contribution to the captive | No
Why it matters: Invoice for the client's required capital contribution to the captive, a standard condition of participation. What to expect: Payment due date is tied to the plan effective date. Confirm wire instructions with Finance before sending funds.
4. FINANCE WORKSTREAM
Not Started | Establish Bank Account for Benefits | Opens the account that funds claims payments | Yes
Why it matters: Open the dedicated bank account used to fund claims payments under the self-funded plan. What to expect: Banks typically need 5-10 business days. Start this early.
Not Started | Review Sample Check Registers | Confirms your claims funding and reporting format | Yes
Why it matters: Review sample TPA check registers to confirm the funding and reporting format Finance will receive going forward. What to expect: One-time review that sets up Finance's ongoing reconciliation process.

## Signing Checklist
Signing Checklist
Prepared for Example Employer, Inc. ¦ New to Self-Funding
Every document below is signed by your CFO or Authorized Signer. Once Setup is finished, click the Applicable filter above and choose Yes to hide anything that doesn't apply.
Status | Item | What This Covers | Applicable? | Due Date
2. DOCUMENTS TO SIGN
Not Started | TPA Admin Service Agreement | The core contract governing claims administration | Yes
Why it matters: The core administrative services contract with the Third Party Administrator. It governs claims processing, customer service, and reporting for the life of the agreement. What to expect: Legal/CFO review is recommended. Typical turnaround is 5-10 business days once terms are finalized.
Not Started | Stop-Loss Quote | Locks in your stop-loss pricing and terms | Yes
Why it matters: The formal quote from the stop-loss carrier confirming premium, specific and aggregate deductibles, and contract basis (paid/incurred vs. incurred/paid). What to expect: Signature confirms acceptance of terms and locks in pricing. Usually due within 5-10 business days of receipt to hold the rate.
Not Started | Stop-Loss Policy | The binding policy that pays claims above deductible | Yes
Why it matters: The binding insurance policy issued after the quote is accepted. This is the legal contract that pays claims above the deductible. What to expect: Issued after the quote is signed and the plan is bound. Review against the quote for accuracy.
Not Started | PBM Master Agreement | Governs pharmacy pricing and rebate terms | Yes
Why it matters: The contract governing pharmacy claims processing, pricing guarantees, and rebate terms with the Pharmacy Benefit Manager. What to expect: Often the longest document in the packet. CFO/Authorized Signer review is recommended before signing.
Not Started | PBM Implementation Manual | Confirms formulary and prior authorization rules | Yes
Why it matters: Operational reference confirming formulary, prior authorization criteria, and member communication timelines for go-live. What to expect: Typically an acknowledgment signature, not a negotiated contract.
Not Started | Captive Agreement | Governs your participation in the group captive | No
Why it matters: The governing agreement (100+ pages) for participation in the group captive, covering member obligations, loss fund mechanics, and governance. What to expect: The most detailed document in the packet. Budget extra review time; CCIG can walk through the key sections before signing.
Not Started | Captive Capital Invoice | Your required capital contribution to the captive | No
Why it matters: Invoice for the client's required capital contribution to the captive, a standard condition of participation. What to expect: Payment due date is tied to the plan effective date. Confirm wire instructions with Finance before sending funds.
Not Started | Savings Engine Agreement - CancerCare | Enrollment agreement with CancerCare | No
Why it matters: Enrollment/services agreement with CancerCare, cancer care navigation and second-opinion support for members with a cancer diagnosis. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - eHealth | Enrollment agreement with eHealth | No
Why it matters: Enrollment/services agreement with eHealth, Medicare and ACA marketplace enrollment support, commonly used for retirees or employees losing group coverage. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - First Stop Health | Enrollment agreement with First Stop Health | No
Why it matters: Enrollment/services agreement with First Stop Health, 24/7 virtual primary and urgent care, giving members phone or video access to a doctor. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Found | Enrollment agreement with Found | No
Why it matters: Enrollment/services agreement with Found, a physician-led weight management program pairing GLP-1 medication access with coaching, aimed at controlling GLP-1 drug spend. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - HUSK | Enrollment agreement with HUSK | No
Why it matters: Enrollment/services agreement with HUSK, a wellness ecosystem covering nutrition counseling, mental health support, and incentive rewards. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Lyra Select | Enrollment agreement with Lyra Select | No
Why it matters: Enrollment/services agreement with Lyra Select, a mental health benefit connecting members to therapy and coaching. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - The Phia Group | Enrollment agreement with The Phia Group | No
Why it matters: Enrollment/services agreement with The Phia Group, benefit compliance and subrogation support, helping recover costs from third parties and reduce plan liability. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Progeny Health | Enrollment agreement with Progeny Health | No
Why it matters: Enrollment/services agreement with Progeny Health, specialized case management for babies in the NICU, aimed at improving outcomes and controlling neonatal claim costs. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Renalogic | Enrollment agreement with Renalogic | No
Why it matters: Enrollment/services agreement with Renalogic, chronic kidney disease and dialysis cost management, identifying at-risk members early and steering care to lower-cost, in-network dialysis providers. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Rightway | Enrollment agreement with Rightway | No
Why it matters: Enrollment/services agreement with Rightway, care navigation and pharmacy guidance, helping members find in-network providers and compare costs for surgeries, imaging, and prescriptions. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - SmartConnect (powered by SmartMatch) | Enrollment agreement with SmartConnect (powered by SmartMatch) | No
Why it matters: Enrollment/services agreement with SmartConnect (powered by SmartMatch), Medicare enrollment support that helps Medicare-eligible employees and retirees compare and enroll in Medicare plans, reducing employer plan spend for that population. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Springbuk | Enrollment agreement with Springbuk | No
Why it matters: Enrollment/services agreement with Springbuk, a health data analytics platform used to identify cost drivers and track plan performance. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Valenz Health | Enrollment agreement with Valenz Health | No
Why it matters: Enrollment/services agreement with Valenz Health, claims cost containment and repricing support, including reference-based pricing and bill review to reduce high-cost claims. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.

## Full Roadmap
Full Roadmap
Prepared for Example Employer, Inc. ¦ New to Self-Funding
Everything in one place: calls, documents, and tasks across every team. Once Setup is finished, click the Applicable filter above and choose Yes to hide anything that doesn't apply.
Status | Item | What This Covers | Responsible Party | Signer | Applicable? | Due Date
1. KICKOFF & IMPLEMENTATION CALLS
Not Started | TPA & Benefit Design Calls | Finalizes plan design and claims setup with your TPA | Client HR + CCIG |  | Yes
Why it matters: Kickoff calls with the Third Party Administrator to finalize plan design, eligibility rules, and claims administration setup ahead of the effective date. What to expect: 2-4 sessions of 60-90 minutes over the first 3-4 weeks. Have current plan documents and eligibility file specs ready.
Not Started | PBM Implementation Calls | Sets up your pharmacy formulary and member ID cards | Client HR + CCIG |  | Yes
Why it matters: Implementation calls with the Pharmacy Benefit Manager to configure the formulary, prior authorization rules, and member ID cards. What to expect: 2-3 calls led by the PBM's implementation team. HR confirms member eligibility feed timing.
Not Started | Cost Containment Vendor Calls | Kicks off each Savings Engine vendor you selected | Client HR + CCIG |  | No
Why it matters: Individual kickoff calls with each selected Savings Engine vendor to set up enrollment, eligibility feeds, and member communications. What to expect: One call per selected vendor, typically 30-45 minutes, scheduled across the first month.
Not Started | COBRA / FSA / HSA Calls | Transitions COBRA and FSA/HSA administration to the new plan | Client HR + CCIG |  | Yes
Why it matters: Setup calls with the COBRA administrator and FSA/HSA vendor to transition existing participants and establish new account administration. What to expect: One call per vendor. HR provides the current COBRA participant list and FSA/HSA balances for transition.
Not Started | Banking Implementation Calls | Sets up claims funding with your TPA and bank | Client Finance + CCIG |  | Yes
Why it matters: Calls with the TPA and bank to set up the claims funding account, wire/ACH authorization, and daily funding process. What to expect: 1-2 calls. Finance should have bank signer authorization ready in advance.
Not Started | Coverage Determination Calls (Optional) | Optional review of how high-cost claims will be paid | Client Finance |  | No
Why it matters: Optional calls where Finance reviews how specific high-cost claims will be adjudicated under the new plan design. What to expect: Scheduled only if Finance opts in on the Setup tab; typically one call.
2. DOCUMENTS TO SIGN
Not Started | TPA Admin Service Agreement | The core contract governing claims administration | Client Executive/Finance | CFO / Authorized Signer | Yes
Why it matters: The core administrative services contract with the Third Party Administrator. It governs claims processing, customer service, and reporting for the life of the agreement. What to expect: Legal/CFO review is recommended. Typical turnaround is 5-10 business days once terms are finalized.
Not Started | Stop-Loss Quote | Locks in your stop-loss pricing and terms | Client Executive/Finance | CFO / Authorized Signer | Yes
Why it matters: The formal quote from the stop-loss carrier confirming premium, specific and aggregate deductibles, and contract basis (paid/incurred vs. incurred/paid). What to expect: Signature confirms acceptance of terms and locks in pricing. Usually due within 5-10 business days of receipt to hold the rate.
Not Started | Stop-Loss Policy | The binding policy that pays claims above deductible | Client Executive/Finance | CFO / Authorized Signer | Yes
Why it matters: The binding insurance policy issued after the quote is accepted. This is the legal contract that pays claims above the deductible. What to expect: Issued after the quote is signed and the plan is bound. Review against the quote for accuracy.
Not Started | PBM Master Agreement | Governs pharmacy pricing and rebate terms | Client Executive/Finance | CFO / Authorized Signer | Yes
Why it matters: The contract governing pharmacy claims processing, pricing guarantees, and rebate terms with the Pharmacy Benefit Manager. What to expect: Often the longest document in the packet. CFO/Authorized Signer review is recommended before signing.
Not Started | PBM Implementation Manual | Confirms formulary and prior authorization rules | Client Executive/Finance | CFO / Authorized Signer | Yes
Why it matters: Operational reference confirming formulary, prior authorization criteria, and member communication timelines for go-live. What to expect: Typically an acknowledgment signature, not a negotiated contract.
Not Started | Captive Agreement | Governs your participation in the group captive | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: The governing agreement (100+ pages) for participation in the group captive, covering member obligations, loss fund mechanics, and governance. What to expect: The most detailed document in the packet. Budget extra review time; CCIG can walk through the key sections before signing.
Not Started | Captive Capital Invoice | Your required capital contribution to the captive | Client Finance | CFO / Authorized Signer | No
Why it matters: Invoice for the client's required capital contribution to the captive, a standard condition of participation. What to expect: Payment due date is tied to the plan effective date. Confirm wire instructions with Finance before sending funds.
Not Started | Savings Engine Agreement - CancerCare | Enrollment agreement with CancerCare | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with CancerCare, cancer care navigation and second-opinion support for members with a cancer diagnosis. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - eHealth | Enrollment agreement with eHealth | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with eHealth, Medicare and ACA marketplace enrollment support, commonly used for retirees or employees losing group coverage. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - First Stop Health | Enrollment agreement with First Stop Health | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with First Stop Health, 24/7 virtual primary and urgent care, giving members phone or video access to a doctor. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Found | Enrollment agreement with Found | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with Found, a physician-led weight management program pairing GLP-1 medication access with coaching, aimed at controlling GLP-1 drug spend. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - HUSK | Enrollment agreement with HUSK | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with HUSK, a wellness ecosystem covering nutrition counseling, mental health support, and incentive rewards. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Lyra Select | Enrollment agreement with Lyra Select | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with Lyra Select, a mental health benefit connecting members to therapy and coaching. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - The Phia Group | Enrollment agreement with The Phia Group | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with The Phia Group, benefit compliance and subrogation support, helping recover costs from third parties and reduce plan liability. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Progeny Health | Enrollment agreement with Progeny Health | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with Progeny Health, specialized case management for babies in the NICU, aimed at improving outcomes and controlling neonatal claim costs. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Renalogic | Enrollment agreement with Renalogic | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with Renalogic, chronic kidney disease and dialysis cost management, identifying at-risk members early and steering care to lower-cost, in-network dialysis providers. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Rightway | Enrollment agreement with Rightway | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with Rightway, care navigation and pharmacy guidance, helping members find in-network providers and compare costs for surgeries, imaging, and prescriptions. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - SmartConnect (powered by SmartMatch) | Enrollment agreement with SmartConnect (powered by SmartMatch) | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with SmartConnect (powered by SmartMatch), Medicare enrollment support that helps Medicare-eligible employees and retirees compare and enroll in Medicare plans, reducing employer plan spend for that population. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Springbuk | Enrollment agreement with Springbuk | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with Springbuk, a health data analytics platform used to identify cost drivers and track plan performance. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
Not Started | Savings Engine Agreement - Valenz Health | Enrollment agreement with Valenz Health | Client Executive/Finance | CFO / Authorized Signer | No
Why it matters: Enrollment/services agreement with Valenz Health, claims cost containment and repricing support, including reference-based pricing and bill review to reduce high-cost claims. What to expect: Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
3. HR WORKSTREAM - OPEN ENROLLMENT SETUP
Not Started | Build HRIS for Open Enrollment | Loads new plan options and rates into your HRIS | Client HR |  | Yes
Why it matters: Configure the HR information system to reflect new plan options, rates, and eligibility rules ahead of open enrollment. What to expect: HR-owned. CCIG provides plan design specs to support setup.
Not Started | Coordinate Open Enrollment Dates/Times | Locks the open enrollment window and meeting schedule | Client HR |  | Yes
Why it matters: Finalize the open enrollment window and schedule employee meetings or webinars. What to expect: Lock this in early; it drives every other communication deadline.
Not Started | Review Open Enrollment Communications & Materials | Approves employee enrollment guides and emails | Client HR |  | Yes
Why it matters: Review and approve employee-facing enrollment guides, emails, and presentation materials before distribution. What to expect: CCIG drafts the first version; HR reviews for accuracy and tone.
Not Started | Complete Open Enrollment Eligibility File | Submits the census file that loads member records | Client HR |  | Yes
Why it matters: Finalize and submit the eligibility census file the TPA and vendors use to load member records. What to expect: The single most time-sensitive HR deliverable. A late file delays ID cards and vendor access for members.
4. FINANCE WORKSTREAM
Not Started | Establish Bank Account for Benefits | Opens the account that funds claims payments | Client Finance |  | Yes
Why it matters: Open the dedicated bank account used to fund claims payments under the self-funded plan. What to expect: Banks typically need 5-10 business days. Start this early.
Not Started | Review Sample Check Registers | Confirms your claims funding and reporting format | Client Finance |  | Yes
Why it matters: Review sample TPA check registers to confirm the funding and reporting format Finance will receive going forward. What to expect: One-time review that sets up Finance's ongoing reconciliation process.
5. COST CONTAINMENT / SAVINGS ENGINE ENROLLMENT
Not Started | Complete Enrollment - CancerCare | Activates CancerCare for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with CancerCare so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - eHealth | Activates eHealth for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with eHealth so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - First Stop Health | Activates First Stop Health for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with First Stop Health so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Found | Activates Found for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Found so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - HUSK | Activates HUSK for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with HUSK so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Lyra Select | Activates Lyra Select for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Lyra Select so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - The Phia Group | Activates The Phia Group for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with The Phia Group so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Progeny Health | Activates Progeny Health for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Progeny Health so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Renalogic | Activates Renalogic for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Renalogic so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Rightway | Activates Rightway for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Rightway so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - SmartConnect (powered by SmartMatch) | Activates SmartConnect (powered by SmartMatch) for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with SmartConnect (powered by SmartMatch) so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Springbuk | Activates Springbuk for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Springbuk so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.
Not Started | Complete Enrollment - Valenz Health | Activates Valenz Health for your members | Client HR |  | No
Why it matters: Finalize the eligibility feed and member enrollment setup with Valenz Health so the solution is active for members at go-live. What to expect: Coordinated on the vendor kickoff call above; exact timing varies by vendor.

## Document & Task Library
Document & Task Library - master content, edit here
Source data behind every client-facing tab. Short Line is the scannable one-liner; Description / What to Expect are the full explanation, shown collapsed by default. Vendor blurbs are drafted from general public information - confirm exact scope with CCIG's vendor relationship before client use.
ID | Phase | Item Name | Type | Applies When (Key) | Responsible Party | Signer | Short Line (scannable) | Description - Why It Matters | What to Expect | CCIG Notes
1 | 1. Kickoff & Implementation Calls | TPA & Benefit Design Calls | Call | ALWAYS | Client HR + CCIG |  | Finalizes plan design and claims setup with your TPA | Kickoff calls with the Third Party Administrator to finalize plan design, eligibility rules, and claims administration setup ahead of the effective date. | 2-4 sessions of 60-90 minutes over the first 3-4 weeks. Have current plan documents and eligibility file specs ready.
2 | 1. Kickoff & Implementation Calls | PBM Implementation Calls | Call | PBM | Client HR + CCIG |  | Sets up your pharmacy formulary and member ID cards | Implementation calls with the Pharmacy Benefit Manager to configure the formulary, prior authorization rules, and member ID cards. | 2-3 calls led by the PBM's implementation team. HR confirms member eligibility feed timing.
3 | 1. Kickoff & Implementation Calls | Cost Containment Vendor Calls | Call | ANY_CC | Client HR + CCIG |  | Kicks off each Savings Engine vendor you selected | Individual kickoff calls with each selected Savings Engine vendor to set up enrollment, eligibility feeds, and member communications. | One call per selected vendor, typically 30-45 minutes, scheduled across the first month.
4 | 1. Kickoff & Implementation Calls | COBRA / FSA / HSA Calls | Call | ALWAYS | Client HR + CCIG |  | Transitions COBRA and FSA/HSA administration to the new plan | Setup calls with the COBRA administrator and FSA/HSA vendor to transition existing participants and establish new account administration. | One call per vendor. HR provides the current COBRA participant list and FSA/HSA balances for transition.
5 | 1. Kickoff & Implementation Calls | Banking Implementation Calls | Call | ALWAYS | Client Finance + CCIG |  | Sets up claims funding with your TPA and bank | Calls with the TPA and bank to set up the claims funding account, wire/ACH authorization, and daily funding process. | 1-2 calls. Finance should have bank signer authorization ready in advance.
6 | 1. Kickoff & Implementation Calls | Coverage Determination Calls (Optional) | Call | FIN_COVERAGE_CALL | Client Finance |  | Optional review of how high-cost claims will be paid | Optional calls where Finance reviews how specific high-cost claims will be adjudicated under the new plan design. | Scheduled only if Finance opts in on the Setup tab; typically one call.
7 | 2. Documents to Sign | TPA Admin Service Agreement | Document | TPA_ADMIN | Client Executive/Finance | CFO / Authorized Signer | The core contract governing claims administration | The core administrative services contract with the Third Party Administrator. It governs claims processing, customer service, and reporting for the life of the agreement. | Legal/CFO review is recommended. Typical turnaround is 5-10 business days once terms are finalized.
8 | 2. Documents to Sign | Stop-Loss Quote | Document | STOP_LOSS | Client Executive/Finance | CFO / Authorized Signer | Locks in your stop-loss pricing and terms | The formal quote from the stop-loss carrier confirming premium, specific and aggregate deductibles, and contract basis (paid/incurred vs. incurred/paid). | Signature confirms acceptance of terms and locks in pricing. Usually due within 5-10 business days of receipt to hold the rate.
9 | 2. Documents to Sign | Stop-Loss Policy | Document | STOP_LOSS | Client Executive/Finance | CFO / Authorized Signer | The binding policy that pays claims above deductible | The binding insurance policy issued after the quote is accepted. This is the legal contract that pays claims above the deductible. | Issued after the quote is signed and the plan is bound. Review against the quote for accuracy.
10 | 2. Documents to Sign | PBM Master Agreement | Document | PBM | Client Executive/Finance | CFO / Authorized Signer | Governs pharmacy pricing and rebate terms | The contract governing pharmacy claims processing, pricing guarantees, and rebate terms with the Pharmacy Benefit Manager. | Often the longest document in the packet. CFO/Authorized Signer review is recommended before signing.
11 | 2. Documents to Sign | PBM Implementation Manual | Document | PBM | Client Executive/Finance | CFO / Authorized Signer | Confirms formulary and prior authorization rules | Operational reference confirming formulary, prior authorization criteria, and member communication timelines for go-live. | Typically an acknowledgment signature, not a negotiated contract.
12 | 2. Documents to Sign | Captive Agreement | Document | CAPTIVE | Client Executive/Finance | CFO / Authorized Signer | Governs your participation in the group captive | The governing agreement (100+ pages) for participation in the group captive, covering member obligations, loss fund mechanics, and governance. | The most detailed document in the packet. Budget extra review time; CCIG can walk through the key sections before signing.
13 | 2. Documents to Sign | Captive Capital Invoice | Document | CAPTIVE | Client Finance | CFO / Authorized Signer | Your required capital contribution to the captive | Invoice for the client's required capital contribution to the captive, a standard condition of participation. | Payment due date is tied to the plan effective date. Confirm wire instructions with Finance before sending funds.
14 | 2. Documents to Sign | Savings Engine Agreement - CancerCare | Document | CC_CANCERCARE | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with CancerCare | Enrollment/services agreement with CancerCare, cancer care navigation and second-opinion support for members with a cancer diagnosis. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
15 | 2. Documents to Sign | Savings Engine Agreement - eHealth | Document | CC_EHEALTH | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with eHealth | Enrollment/services agreement with eHealth, Medicare and ACA marketplace enrollment support, commonly used for retirees or employees losing group coverage. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
16 | 2. Documents to Sign | Savings Engine Agreement - First Stop Health | Document | CC_FIRSTSTOP | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with First Stop Health | Enrollment/services agreement with First Stop Health, 24/7 virtual primary and urgent care, giving members phone or video access to a doctor. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
17 | 2. Documents to Sign | Savings Engine Agreement - Found | Document | CC_FOUND | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with Found | Enrollment/services agreement with Found, a physician-led weight management program pairing GLP-1 medication access with coaching, aimed at controlling GLP-1 drug spend. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
18 | 2. Documents to Sign | Savings Engine Agreement - HUSK | Document | CC_HUSK | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with HUSK | Enrollment/services agreement with HUSK, a wellness ecosystem covering nutrition counseling, mental health support, and incentive rewards. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
19 | 2. Documents to Sign | Savings Engine Agreement - Lyra Select | Document | CC_LYRA | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with Lyra Select | Enrollment/services agreement with Lyra Select, a mental health benefit connecting members to therapy and coaching. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
20 | 2. Documents to Sign | Savings Engine Agreement - The Phia Group | Document | CC_PHIA | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with The Phia Group | Enrollment/services agreement with The Phia Group, benefit compliance and subrogation support, helping recover costs from third parties and reduce plan liability. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
21 | 2. Documents to Sign | Savings Engine Agreement - Progeny Health | Document | CC_PROGENY | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with Progeny Health | Enrollment/services agreement with Progeny Health, specialized case management for babies in the NICU, aimed at improving outcomes and controlling neonatal claim costs. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
22 | 2. Documents to Sign | Savings Engine Agreement - Renalogic | Document | CC_RENALOGIC | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with Renalogic | Enrollment/services agreement with Renalogic, chronic kidney disease and dialysis cost management, identifying at-risk members early and steering care to lower-cost, in-network dialysis providers. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
23 | 2. Documents to Sign | Savings Engine Agreement - Rightway | Document | CC_RIGHTWAY | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with Rightway | Enrollment/services agreement with Rightway, care navigation and pharmacy guidance, helping members find in-network providers and compare costs for surgeries, imaging, and prescriptions. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
24 | 2. Documents to Sign | Savings Engine Agreement - SmartConnect (powered by SmartMatch) | Document | CC_SMARTCONNECT | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with SmartConnect (powered by SmartMatch) | Enrollment/services agreement with SmartConnect (powered by SmartMatch), Medicare enrollment support that helps Medicare-eligible employees and retirees compare and enroll in Medicare plans, reducing employer plan spend for that population. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
25 | 2. Documents to Sign | Savings Engine Agreement - Springbuk | Document | CC_SPRINGBUK | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with Springbuk | Enrollment/services agreement with Springbuk, a health data analytics platform used to identify cost drivers and track plan performance. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
26 | 2. Documents to Sign | Savings Engine Agreement - Valenz Health | Document | CC_VALENZ | Client Executive/Finance | CFO / Authorized Signer | Enrollment agreement with Valenz Health | Enrollment/services agreement with Valenz Health, claims cost containment and repricing support, including reference-based pricing and bill review to reduce high-cost claims. | Signature authorizes data sharing and enrollment. Turnaround varies by vendor; confirm on the vendor kickoff call.
27 | 3. HR Workstream - Open Enrollment Setup | Build HRIS for Open Enrollment | Task | ALWAYS | Client HR |  | Loads new plan options and rates into your HRIS | Configure the HR information system to reflect new plan options, rates, and eligibility rules ahead of open enrollment. | HR-owned. CCIG provides plan design specs to support setup.
28 | 3. HR Workstream - Open Enrollment Setup | Coordinate Open Enrollment Dates/Times | Task | ALWAYS | Client HR |  | Locks the open enrollment window and meeting schedule | Finalize the open enrollment window and schedule employee meetings or webinars. | Lock this in early; it drives every other communication deadline.
29 | 3. HR Workstream - Open Enrollment Setup | Review Open Enrollment Communications & Materials | Task | ALWAYS | Client HR |  | Approves employee enrollment guides and emails | Review and approve employee-facing enrollment guides, emails, and presentation materials before distribution. | CCIG drafts the first version; HR reviews for accuracy and tone.
30 | 3. HR Workstream - Open Enrollment Setup | Complete Open Enrollment Eligibility File | Task | ALWAYS | Client HR |  | Submits the census file that loads member records | Finalize and submit the eligibility census file the TPA and vendors use to load member records. | The single most time-sensitive HR deliverable. A late file delays ID cards and vendor access for members.
31 | 4. Finance Workstream | Establish Bank Account for Benefits | Task | ALWAYS | Client Finance |  | Opens the account that funds claims payments | Open the dedicated bank account used to fund claims payments under the self-funded plan. | Banks typically need 5-10 business days. Start this early.
32 | 4. Finance Workstream | Review Sample Check Registers | Task | ALWAYS | Client Finance |  | Confirms your claims funding and reporting format | Review sample TPA check registers to confirm the funding and reporting format Finance will receive going forward. | One-time review that sets up Finance's ongoing reconciliation process.
33 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - CancerCare | Task | CC_CANCERCARE | Client HR |  | Activates CancerCare for your members | Finalize the eligibility feed and member enrollment setup with CancerCare so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
34 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - eHealth | Task | CC_EHEALTH | Client HR |  | Activates eHealth for your members | Finalize the eligibility feed and member enrollment setup with eHealth so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
35 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - First Stop Health | Task | CC_FIRSTSTOP | Client HR |  | Activates First Stop Health for your members | Finalize the eligibility feed and member enrollment setup with First Stop Health so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
36 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - Found | Task | CC_FOUND | Client HR |  | Activates Found for your members | Finalize the eligibility feed and member enrollment setup with Found so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
37 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - HUSK | Task | CC_HUSK | Client HR |  | Activates HUSK for your members | Finalize the eligibility feed and member enrollment setup with HUSK so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
38 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - Lyra Select | Task | CC_LYRA | Client HR |  | Activates Lyra Select for your members | Finalize the eligibility feed and member enrollment setup with Lyra Select so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
39 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - The Phia Group | Task | CC_PHIA | Client HR |  | Activates The Phia Group for your members | Finalize the eligibility feed and member enrollment setup with The Phia Group so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
40 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - Progeny Health | Task | CC_PROGENY | Client HR |  | Activates Progeny Health for your members | Finalize the eligibility feed and member enrollment setup with Progeny Health so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
41 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - Renalogic | Task | CC_RENALOGIC | Client HR |  | Activates Renalogic for your members | Finalize the eligibility feed and member enrollment setup with Renalogic so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
42 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - Rightway | Task | CC_RIGHTWAY | Client HR |  | Activates Rightway for your members | Finalize the eligibility feed and member enrollment setup with Rightway so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
43 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - SmartConnect (powered by SmartMatch) | Task | CC_SMARTCONNECT | Client HR |  | Activates SmartConnect (powered by SmartMatch) for your members | Finalize the eligibility feed and member enrollment setup with SmartConnect (powered by SmartMatch) so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
44 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - Springbuk | Task | CC_SPRINGBUK | Client HR |  | Activates Springbuk for your members | Finalize the eligibility feed and member enrollment setup with Springbuk so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.
45 | 5. Cost Containment / Savings Engine Enrollment | Complete Enrollment - Valenz Health | Task | CC_VALENZ | Client HR |  | Activates Valenz Health for your members | Finalize the eligibility feed and member enrollment setup with Valenz Health so the solution is active for members at go-live. | Coordinated on the vendor kickoff call above; exact timing varies by vendor.

## Project Tracker
Project Tracker
| Client | Example Employer, Inc.
| Engagement Type | New to Self-Funding
| Prepared By | CCIG Benefits Team
Date Prepared
SCOPE SUMMARY (applicable items only)
| Category | Count
| Documents to Sign | 5
| HR Calls & Tasks | 7
| Finance Calls & Tasks | 3
STATUS ACROSS FULL ROADMAP (applicable items only)
| Status | Count
| Not Started | 15
| In Progress | 0
| Complete | 0
| N/A | 0